## task_list
	Configure laptop so it does not suspend when lid is closed					Latest issues
	Build LoRa radio control					Get data into plotjuggler or something like that so I can analyze the steering correction
	Initial test of LoRa radio control with steering					5 amp fuse blows on ignition - check before shutting down - test eswitch, manual and ignition shutdown
	Initial test of LoRa radio control with throttle					USB hub is putting 5v into power bar when master power is off - coming from laptop USB
	Secure laptop to electronics board
	Connect estop to relay board
	Install emergency stop button
	test the estop with the relay and radio control unit
	Garage test of throttle
	Field test of throttle and steering
	Install USB hub
	temporarily install GPS with antennae
	Test GPS to ensure it is publishing data with ROS nmea_navsat_driver
	Start base station and get RTK fix
	ROS AG version of nmea_navsat_driver - install and update to publish heading so gps_odom.py will work
	Update software to publish ticks for rear wheels
	Install "Jeff's simulator" on tractor laptop
	Install ROS IMU including reset software from Chip Robotics
	Craft a script to run the current modules
	Run gps_odom.py and check frames.py
	Get the TF tree looking correct (e.g. map -> odom -> base_footprint -> base_link -> gps)
	Resolve if you are launching gps_odom from launch file or rosrun in ros_start.sh
	Get movebaseflex to produce cmd_vel data
	Create .png map file; Adjust gps_odom.py and determine correct origin for .yaml file

	Move tractor back inside
	Remove existing battery
	Make device so you can charge them in the 18650 charger
	Test capacity of existing batteries

	Manually drive the tractor around the yard and check path against the .png file
	Choose positions to test A B test

	Test showing updated map file and establish origin position
	Install ROSAg simulator on clean laptop
	Move the tractor antanae around and see what the x, y coordinates are
	Make manual statements to go the x, y coordinates that you are certain of
	Look where “[INFO] [1670590414.456635]: Bad GPS status - data.status.status: 0” is published in driver.py and produce some sort of summary statement and switch to dead reckoning
	Install RTK base on pole
	Steering tuning
	Install 12V to 19V power for laptop
	Determine ROS navigation unit of measure for throttle/speed control
	Implement 12V battery monitor on tractor and feed to RC controller
	Make permanent holder for PTO engage handle
	Get data out of TTGO board and into ROS messages
	Cover for electronics
	Digital control of engine throttle

Old task list	Task Description
Step	Install ROS on laptop	Al	Collen	Jim	Sohin	Ross	Notes
1	(Optional) Install Turtlesim and Stage and drive with gamepad on laptop	Complete	Complete		complete	Complete	Connect RPi to Wifi: https://www.raspberrypi.org/documentation/configuration/wireless/wireless-cli.md Setup as ROSMASTER https://github.com/mktk1117/six_wheel_robot/wiki/Communication-between-Raspberry-Pi-and-PC-(ROS)
2	(Optional) Install Turtlebot on laptop	Complete			skipped
3	Install ROS-Ag lawn tractor simulator	Complete			skipped		Install Turtlebot and stage: http://wiki.ros.org/action/show/turtlebot/Tutorials/indigo/Turtlebot%20Installation?action=show&redirect=turtlebot%2FTutorials%2Findigo%2FInstallation
4	RPi load the Ubiquity robot image and ROS	Complete			skipped
5	Set up VPN access to RPi and laptop	Complete	Ordering		skipped
6	Order steering control motor, estop and angle sensor	Complete		Pi 3B on hand	skipped
12	Desk check motor, motor driver and Teensy	Complete
7	Flash Teensy with code and test motor controller	Complete
7.1	Test motor	Complete
7.2	Deskcheck steering angle sensor	Complete
7.3	Test controlling the motor using twist commands	Complete
7.5	Flash Teensy and deskcheck wheel speed encoders	complete
7.6	Place order for GPS, IMU and related tools
8	Test GPS and IMU connectivity and packages including getting robot localization working	complete			complete
9	In alternate vehicle test drive, log ROS bag file	in progress			In progress
10	Buy lawn tractor (e.g. Cub Cadet XT1 18Hp) (Collen: Hasquavarna 18hp)
11	Fabricate bracket for steering motor	Complete	Complete
13.1	Fabricate bracket for steer angle sensor	complete
13.2	Fabricate bracket for wheel speed encoders	complete
13.3	Test controlling 8 channel relay from RPi	complete
14	Install steering motor
15	Install angle sensor	complete
16	Test steering control	complete
18.1	Install actuator to control transmission	complete
17	Order equipment to capture wheel speed	complete
19	Install wheel speed capture device	complete
20	Test transmission control	complete
18.2	Test pickup sensor wheel speed / odometry	complete
7.4	Create wiring harness and electronics board	complete
21	Install estop	complete
22	Install gas tank, battery and fuel control valve	complete
23	Test starting motor and controls	complete
24	Update URDF file using URDF helper spreadsheet	complete
25	Field test - Test steering control, capture steering performance data
26	Install actuator to control engine throttle	complete
27	Update localization with odometry data
28	Test AB line performance	In process
29	Test a more robust diagnostic node (See Sohin's work) (e.g. test for wheels spinning, )
30

Additional tasks to consider	Setup communications (radio, cell, flag semaphore) - maybe with VPN, maybe with Ubiquity Networks or Microtek - so we will need to set a standard

A draft set of revised steps	Buy components to get started.
0	Mount electrical components on control board		https://www.cubcadet.com/equipment/cubcadet/power-steering-kit-62800-119-0001p
1	Remove un-needed parts from vehicle
2	Mount steering motor
3	Mount transmision control actuator
4	Install safety kill switches
5	Download the RPi ubiquity image; Install vncserver; Set up wi-fi;
6	In the visualizer, use keyboard teleop nodes to drive the tractor
7	In the visualizer, use Logitech gampad to drive the tractor
8	In the visualizer, use Logitec gampad connected to an Rpi to drive the tractor visualized on my laptop on the same wi-fi network
9	Connect GPS and show the tractor in the visualizer at my current GPS position
10	Connect IMU and visualize the results
11	Test localization combining IMU and GPS data using simple GPS
12	Test steering using ROS published steering commands
13	Test reading analog data from JRK of the potentiometer
14	Log the angular and forward velocity of my tractor from the IMU - To log data: $ rosbag record -a (records all topics) /vel /imu; To play back with RQT: $ rosbag play -l <filename> $ rqt
15	Confirm kill switch operates
16	Connect a microcontroller to my laptop and test steer my tractor using the gamepad
17	Connect GPS to laptop on the rover and confirm GPS signal is being received.
18	What vehicle specific parameters need to be known and input at this point?
19	Run 2 waypoint AB line test with 2 lat/lon cooridinates . The cross track error should be +/- 2 inches.
20	Replay AB line test with the ability to look at key variables (e.g. cross track error and steering PWM signals that were sent)
21	Run a multi waypoint test with at least 10 lat/lon cooridinates with only steering control while I'm on the tractor for safety while logging data.
22	Connect the Arduino to my companion computer and test throttle control using the gamepad
23	Craft a mission plan for a field giving basic information about the field and the type of path I want to run.
24	Simulate running a mission plan for a given field.
25	Run a multi waypoint test with at least 10 lat/lon cooridinates with steering control and throttle while I'm on the tractor for safety while logging data.
26	Run a multi waypoint test with at least 10 lat/lon cooridinates with steering, throttle and brake control while I'm on the tractor for safety while logging data.
27	Run a defined mission with steering, throttle and brake control.
28	Install camera feed into RPi and check CPU utilization
29
	Run a simulation showing an example tractor running 4 waypoints with a Google map or similar visual. Similar to this example in Dronekit http://python.dronekit.io/examples/guided-set-speed-yaw-demo.html (e.g. Have a launch file it reads WPs in a config file and would automatically start the drive. This could be a Jupyter notebook that has a run/play button or just a launch file.) The user might be encouraged to input their own wps for fun.)

## Bill of material
Bill of material

	Item	Category	Mfg	Description	Supplier	Cost	Reference
	1	vehicle	Cub Cadet	42" mower with 18HP Kohler engine	Home Depot	$1,650
		steering		12 volt power steering motor	ebay	$50
		transmission		linear actuator

		steering		motor controller			Investigate using a Sabertooth controller and py lib (https://github.com/MomsFriendlyRobotCompany/pysabertooth); See also https://www.dimensionengineering.com/datasheets/Sabertooth2x25v2.pdf
		safety		wireless kill switch and transmitter
		safety		lanyard kill switch
		electronics		RPi 3 for companion computer
		electronics	Tinkerforge	IMU Brick 2	Tinkerforge
		electronics		Ppowered USB hub
		electronics		RTK GNSS module and antennae
		electronics		Terminal wiring blocks
				5 color wire (18 AWG)

Version 2 Items to consider
				https://www.cubcadet.com/equipment/cubcadet/power-steering-kit-62800-119-0001p

## Al Jones Cub Cadet
Bill of Material
Item	Group	Category	Mfg	Description	Supplier	Cost	Reference
15	0.1	electrical		5 color wire (18 AWG)
		electrical	Cofufu	Dual Row 8 Position Screw Terminal Strip	Amazon	$15	https://www.amazon.com/gp/product/B01DY73N2C/ref=ox_sc_act_title_1?smid=A31P8DECE97940&psc=1
		electrical		Blade fuses	Amazon	$11	https://www.amazon.com/FICBOX-Standard-Assorted-Automotive-Replacement/dp/B074FSMTT6/ref=sr_1_9?hvadid=177781729677&hvdev=c&hvlocphy=9005829&hvnetw=g&hvpos=1t1&hvqmt=e&hvrand=5603582245898726375&hvtargid=aud-647006051489%3Akwd-38221990790&keywords=5+amp+blade+fuse&qid=1553465023&s=gateway&sr=8-9
		electrical		Male to Male Jumper Wires	Amazon	$7	https://www.amazon.com/gp/product/B01IB7UOFE/ref=ppx_yo_dt_b_asin_title_o00_s00?ie=UTF8&psc=1
	0.1	electrical	Hilitchi	Hilitchi Ceramic Chip Capacitors Kit	AMazon	$19	https://www.amazon.com/gp/product/B0734RHL8S/ref=ppx_od_dt_b_asin_title_s00?ie=UTF8&psc=1
				Insulated #6 Size Fork Terminal 22-18 Gauge	Amazon	$7	https://www.amazon.com/gp/product/B01B17DL0G/ref=ppx_yo_dt_b_asin_title_o03_s02?ie=UTF8&psc=1
				Phillips Rounded Head Screws #4 x 3/8" (100)	mcmaster.com	$11	https://www.mcmaster.com/92470a108
			iKits	Short Micro USB Cable	Amazon	$14	https://www.amazon.com/gp/product/B01CU6MTF0/ref=ppx_yo_dt_b_asin_title_o03_s00?ie=UTF8&psc=1
				#4 x 3/8 pan head screws	Home Depot
4	0.2	angle sensor		steering gear to drive potentiometer	Amazon	$9	https://smile.amazon.com/gp/product/B004XVGD3K/ref=pe_2313360_292132620_em_1p_0_ti
21	0.2	electrical		10-Way Blade Fuse Block	Amazon	$12	https://www.amazon.com/dp/B00QMULSUI/ref=cm_sw_r_cp_ep_dp_ztrlBb74RC149
20	0.2	electrical		Battery Terminal Switch Quick Cut-off	Amazon	$9	https://www.amazon.com/dp/B00GJMDTH4/ref=cm_sw_r_cp_ep_dp_fnrlBbSSCZNBG
10	0.2	electronics	Raspberry Pi	RPi 3 model B (2) rover+controller	Amazon	$76	https://www.amazon.com/Raspberry-Pi-RASPBERRYPI3-MODB-1GB-Model-Motherboard/dp/B01CD5VC92/ref=sr_1_1?s=electronics&ie=UTF8&qid=1540036817&sr=1-1&keywords=RPi
12	0.2	electronics	APANAGE	Powered USB hub	Amazon	$37	https://www.amazon.com/Splitter-Transfer-Charging-Individual-Switches/dp/B07DW646GY/ref=sr_1_3?keywords=apanage+usb+powered+hub&qid=1558977932&s=gateway&sr=8-3-spell
14	0.2	electronics	uxcell	Terminal wiring blocks	Amazon	$0	https://www.amazon.com/gp/product/B01MG7EU60/ref=oh_aui_search_asin_title?ie=UTF8&psc=1
				Resitor (10K)
				Capacitor (0.1uf)
23	0.2	electronics	Logitech	Gampad controller for teleop	Amazon	$20	https://www.amazon.com/Logitech-940-000110-Gamepad-F310/dp/B003VAHYQY/ref=sr_1_2?ie=UTF8&qid=1540039077&sr=8-2&keywords=logitech+gamepad
22	0.2	fuel		Fuel Shut-Off Valve	Amazon	$0	https://www.amazon.com/dp/B0038U3JKM/ref=cm_sw_r_cp_ep_dp_JlrlBbDTAR8AM
	0.2	fuel		Fuel Line Hose 5/16 Inch Inside Diameter	Amazon	$0	https://www.amazon.com/gp/product/B06XWQXYNY/ref=ox_sc_act_title_1?smid=A2D2R1XTPRDL5U&psc=1
	0.2	fuel	Osias	fuel pump in-line 2.5 psi	Amazon	$0	https://www.amazon.com/OSIAS-Universal-Pressure-Electric-HEP-02A/dp/B01J7TX18C/ref=sr_1_12?keywords=HEP02A+fuel+pump&qid=1551544497&s=automotive&sr=1-12
28	0.2	odometry	AMS	AS5048B Magnetic Position Sensor development board	Mouser	$32	https://www.mouser.com/ProductDetail/ams/AS5048B-TS_EK_AB?qs=%2Fha2pyFadugmE0RHmzPjrQJsc8R62r5OqqOYThLMeLtq4qen32RnAA%3D%3D
		odometry	PJRC.com	Teensy 3.2	PJRC.com	$20	https://www.pjrc.com/store/teensy32.html
		odometry	XiKe	5x16x5mm Double Rubber Seal Bearings	Amazon	$10	https://www.amazon.com/gp/product/B071RXC7FV/ref=ppx_yo_dt_b_asin_title_o01_s00?ie=UTF8&psc=1
8	0.2	safety		wireless kill switch and transmitter	Amazon	$22	https://www.amazon.com/Logisys-RM01-Wireless-Control-Keychains/dp/B000MXNJ7G
9	0.2	safety		lanyard kill switch	Amazon	$9	https://www.amazon.com/Sea-Dog-420488-1-Switch-Lanyard/dp/B00DH3QHBI/ref=sr_1_4?ie=UTF8&qid=1540036469&sr=8-4&keywords=kill+switch+lanyard
7	0.2	steering	Cytron	30 amp motor controller	Amazon	$36	https://www.amazon.com/gp/product/B01M4PXFBG/ref=oh_aui_search_asin_title?ie=UTF8&psc=1
	0.2	electronics	Elegoo	8 Channel DC 5V Relay Module	Amazon	$9	https://www.amazon.com/Elegoo-Module-Optocoupler-Arduino-Raspberry/dp/B01HCFJC0Y/ref=sr_1_6?keywords=8+channel+relay&qid=1551460552&s=gateway&sr=8-6
11	0.3	electronics	Tinkerforge	IMU Brick 2	Tinkerforge	$80	https://www.tinkerforge.com/en/shop/bricks/imu-v2-brick.html
16	0.4	electronics	pjrc.com	Teensy 3.5	PJRC	$25	https://www.pjrc.com/store/
2	0.5	steering	Denso/Koyo	12 volt DC power steering motor	ebay	$80	2005-2011 Chevrolet Cobalt Pursuit HHR G5 Electric Power Steering Pump Motor OEM
				Ultrasonic Distance Measuring Transducer (4)	ebay	$29	https://www.ebay.com/itm/172267770126
17	0.6	steering		16.5mm-36 to 3/4″ Smooth U-Joint	epowersteering.com	$80	http://www.epowersteering.com/purchase/product/16-5mm-36-to-34-smooth-u-joint
	0.6	steering		Mounting bracket for steering motor	epowersteering.com	$82	http://www.epowersteering.com/purchase/product/bracket-style-a/
5	0.7	angle sensor		potentiometer	Mouser	$23	SPECTROL MODEL 533 2K OHM 3-TURN https://www.mouser.com/ProductDetail/Vishay-Spectrol/533B1202JC?qs=M7yXsciANIWZWrNVgEyeOQ%3d%3d or https://www.digikey.com/product-detail/en/vishay-spectrol/533B1502JC/533B1502JC-ND/1287408&?gclid=CjwKCAjwpKveBRAwEiwAo4Pqm2QY-RDetcg1h5KuqWSZLY3JSz8iQa7xGcRnCGdu2W_cf9AKyApkxRoCwjwQAvD_BwE
1	1	vehicle	Cub Cadet	XT1 42" mower with 18HP Kohler engine	Home Depot	$1,650
24	2.1	electrical	Molex	CONN RECEPTACLE 9POS .084	DigiKey	$2	https://www.digikey.com/product-detail/en/molex-llc/0050842090/WM1251-ND/134556
25	2.1	electrical	Molex	CONN PLUG 9POS .084	DigiKey	$2	https://www.digikey.com/products/en?keywords=WM1250-ND
26	2.1	electrical	Molex	CONN TERM FEMALE 14-20AWG TIN	DigiKey	$2	https://www.digikey.com/products/en?keywords=WM1271-ND
27	2.1	electrical	Molex	CONN TERM MALE 14-20AWG TIN	DigiKey	$2	https://www.digikey.com/products/en?keywords=WM1270-ND
18	2	odometry		gear			see picture Matt sent; Sourced at local farm store.
19	2	odometry		sensor
3	2.2	steering	Cub Cadet	steering shaft to be trimmed down	Cub Cadet	$42	https://www.cubcadet.com/equipment/ProductDisplay?storeId=10051&productId=1847321&urlRequestType=Base&langId=-1&catalogId=14101
6	2.3	transmission		SUPER200 High Torque Metal Servo	ebay	$64	https://www.ebay.com/itm/SUPER200-High-Torque-Metal-Servo-12-24V-200kg-cm-0-5S-60-Degree-BEC-5V-f-Robot-/351765086900
	2.4	transmission	Ask The Mechanic co.uk	M6 Threaded Stud Rod Link	ebay	$0	https://www.ebay.co.uk/itm/263310719741
	2.3	transmission		6mm Male 6mm Female Thread L Shaped Ball Joint	ebay	$0	https://www.ebay.com/itm/6mm-Male-6mm-Female-Thread-L-Shaped-Ball-Joint-Rod-End-Bearing-6Pcs/391196104622?ssPageName=STRK%3AMEBIDX%3AIT&_trksid=p2057872.m2749.l2649
	2.5	transmission	Home Depot	1" Aluminum strip	Home Depot
	2.5	transmission	McMasterCarr	Head Hex Drive Screw, 8-32 Size, 3/4" Long	McMasterCarr	$7	https://www.mcmaster.com/92949a197
	2.5	transmission	McMasterCarr	Nylon-Insert Locknut, 8-32 Thread Size	McMasterCarr	$6	https://www.mcmaster.com/91831a009
	2.5	transmission	McMasterCarr	Washer for Number 8 Screw Size, 0.172" ID, 0.375" OD	McMasterCarr	$2	https://www.mcmaster.com/92141a009
13	3.1	GPS	Comnav	K706 RTK GNSS module and interface board (2)	Comnav	$2,340
	3.2	GPS		CORS RTK GNSS Survey Antenna	ebay	$200	https://www.ebay.com/itm/CORS-RTK-GNSS-Survey-Antenna-high-gain-measurement-GNSS-GPS-GLONASS-BDS/253786590956?ssPageName=STRK%3AMEBIDX%3AIT&_trksid=p2060353.m2749.l2649

					Total	$5,103
					EFI engine label
Cub Cadet Info
Tractor 1 (PA)		Model: 13A9A1CS256			parts tree link	cub cadet link	https://www.partstree.com/brands/cub-cadet/lawn-garden-tractors-series-xt1-enduro/
Tractor 2 (TX)		Model: 13APA1CT056

Notes on detail steps
		Cut steering shaft to 150 mm (needs to be confirmed)
		Install rough cut brackets to hold motor
		Finalize basic bracket system for steering
		Contact fabricator to make a production version
		Angle sensor - get correct nut to hold potentiometer - determine what size it is - 3D print it
		Rough position for transmission control servo
		Fabricate connector between servo and transmission
		Install servo for transmission control
		Make and install battery holder
		Make and install gas tank holder
		Make and install flat sheet to mount electronics and holder cutting deck handle
		Make and install cutting deck handle
		Buy board to use as draft electronics board
		Layout components
		Make standoff to hold RPi and 8 Channel relay (#4 3/8" .3" high)
		Install sublime on RPi to edit software to test 8 channel relay
		Connect the RPi and 8 channel controller, test the software control
		Make holder for Teensy 3.5 and wire hub
		Crimp wires for Teensy and wire hub 1 based on colors in wiring connections
		Make holder for wi-fi (JetPack)
		Mount Teensy holder
		Solder Teensy and crimp wires to wire hub
		Make 4 standoffs to hold IMU (#4 3/8" .3" high)
		Mount the IMU
		Mount JetPack Holder
		Angle sensor - determine bracket dimensions for the bottom of the bracket (holes 21 mm apart and 6.35 mm in diameter)
		Angle sensor - determine bracket dimensions for the top of the bracket, join and mount
		Size hole on half moon gear, - hole is c 4.72-4.76 (4.74 for me) mm x 10 mm (H) - your printer may vary
		Determine the size of the circle to fit over the 9/16" bolt in the half moon gear - 16.30 seems best X 7mm (H) (hex bolt is near 7.15 - 7.2r for 6 sided polygon)
		determine knob size for magnet holder 12.05 seems good for testing
		Make shaft to hold magnet, get length correct - 53.65 is the best length I believe
		Determine bracket length 60+37, depth and angle to second hole for magnetic reader; glued 2 pieces together to get basic angle; get hole diameter clarified also
		Get small screws for AS5600 contactless potentiometer (smaller than #4)
		Make base holder for magnetic reader with 2 holes 21 mm apart and a part coming up 20 mm with screw holes in it. - abandon - move to mounting on bolt head
		Make AS5600 (version 1) holder attaching it to the 9/16" hex head bolt
		Test AS5600 using OEM Windows software
		Make test stand for AS5600
		Test holder for separate magnet (6.1 is tight; 6.2 also work, but would like come loose with vibration) - maybe try 6.15
		Read sensor from Arduino
		Load Teensy from Windows machine for first run (Step 7 - Teensy Hello World)
		Load Teensy from RPi (Step 7.1)
		Connect SDA/SCL wires from terminal adapter to Teensy
		Connect USB hub 5V to terminnal adapter to supply AS5600
		Connect wires from angle sensor to Teensy
		Mount 12 volt blade fuse holder
	4/27/19	Connect the 12 volt supply to the board
	4/27/19	Get angle sensor to stick to the circular washer - trying epoxy
	4/27/19	Produce hello world message from Teensy using ROS and report usign ROSSERIAL and "chatter" topic
	4/28/19	Connect u-joint with bolt to steering rod before welding
	4/30/19	Reduce the sample AS5600 code down to essential code; Test on Arduino
	5/3/19	Debug AS5600 test program - remove bad statement
	5/4/19	Add 4.7K pullup resistor to Teensy (3.3V to 2 resitors to pin 18 and 19)
		Test Teensy Blink (test1_blink.cpp) and Chatter (test2_chatter_v2)
	5/6/19	Install motor, motor drive and connect to Teensy
	5/7/19	Update test AS5600 to make reading sensor a routine instead of inside the loop function
	5/10/19	Test AS5600 test (test3_read_AS5600) passing understandable data from angle sensor to ros topic
	5/11/19	Make magnet holder for front axle (6.1 mm) and filler washer
	5/11/19	Cytron bracket - Cut brace and drill holes
	5/12/19	Mount Cytron and Teensy to motor bracket (install bar across, determine correct screw and hole size, make mount and cover)
	5/19/19	Write steering control program that tests multi-points and cycles through them
	5/19/19	Build test bed for SuperServo
	5/19/19	Adjust angle sensor on Super Servo to give greatest possible range
	5/23/19	Program Teensy 3.2 with Matt's failsafe program and test
	5/24/19	Solder wires from SuperServo to Teensy and confirm behavior using testbed
	5/24/19	Install SuperServo on lawn tractor
	5/25/19	Get nylon nuts to hold SuperServo and transmission control brackets in place (#8 for servo,
	5/25/19	Reinstall the electronics; Extend 12V cables; Get ready for testing starting the motor.
	5/25/19	Extend the ground cable from the battery to the grounding position
	5/26/19	Extend the positive 12V cable from the solenoid to the battery
	5/26/19	Test grounding magnetto wire (yellow into engine) to ground for engine stop
	5/26/19	See if you have any molex pins or remover to test removing a pin; If not, order kit
	6/1/19	Install kill switch # 1 on vehicle
	6/1/19	Make test program to listen to cmd_vel rostopic
	6/1/19	Run test_sweep program on Teensy on tractor
	6/8/19	Write test program with double point map function to convert linear.x to microseconds
	6/8/19	3D print servo arm to maximize pwm for reduced sweep
	7/4/19	Build test bed for SuperServo using 2X4 to hold servo and suitcase scale
	7/7/19	Install bootloader on STM32 and upload blink
	7/7/19	Confirm exact dimensions for Teensy holder for odom holder (hole spacing is 56X36)
	7/7/19	Adjust 3D model for AS5048 holder and print it
	7/7/19	Solder the protoboard for Teensy and AS5048
	7/7/19	Run I2C scanner to make sure you can see the AS5048 on the protoboard
	7/7/19	Confirm position of AS5048 chip in order to set the mounting position on the protoboard
	7/14/19	3D print the rear sensor speed detector and install protoboard
	7/14/19	Update 3D model for axle gear to include a set screw
	7/15/19	Install ZeroTier on new laptop and connect to Odom Teensy
	7/15/19	Ready to test odom - program hello world and test ROS publish routine
	7/20/19	Ready to test odom - connect Teensy to USB hub and confirm you can program and read
	7/20/19	Change the 3D model to accomodate bearing for shaft of gear
	7/22/19	Solder AS5048 to protoboard and ensure the distance to magnet is correct
	7/22/19	Make a new SuperServo with only a USB connector that listens to odom
	7/22/19	Remove old wiring from SuperServo and connect Teensy
	7/22/19	Test Teensy driving the SuperServo with Arduin IDE (sending three signals - neutral, forward, reverse) - SuperServo_Teensy_32_test1
	7/25/19	Order special bolts to connect the servo with allen wrench heads
	7/26/19	Set up udev for Transmission_control
	7/27/19	Test sweep program on Teensy/Super_Servo with PlatformIO
	7/27/19	Make box to hold potentiometer
	7/27/19	Get teensy for joystick/pot device and program with blink
	7/28/19	Setup DIY joystick / potentiometer to output cmd_vel linear.x and angular.z
	7/28/19	Setup the SuperServo Teensy to read cmd_vel and sweep arm to connect it to the control arm
	7/28/19	Test PWM values for neutral and to connect the transmission control arm
	7/28/19	Ready to test odom - jack up rear wheels, run transmission
	7/28/19	Test basic tranmission control
	8/3/19	Update the launch file to start the left_odom sensor; move to RPi; Launch and echo results
	8/3/19	Recover udev rules for Teensy devices
	8/3/19	Create workaround to avoid PlatformIO crashing Teensy's
	8/3/19	Reprogram DIY joystick (update platformio with env:teensy35 and potentiometer_control; upload firmware: pot_to_cmd_vel_publisher_2.cpp)
	8/3/19	Reprogram speed sensor(update platformio with env:teensy31 and odom_left; upload firmware: as5048B_speed_sensor_left.cpp)
	8/4/19	Reprogram transmission control (update platformio with env:teensy31 and transmission_control; upload firmware: superservo_control_failsafe.cpp)
	8/4/19	Problem: transmission not under joystick control					launch files and look if cmd_vel is publishing; then put info statment in transmission control
	8/9/19	Confirm 1303 is still a good point for neutral - now 1290
	8/17/19	Test using unbind/bind to "turn off" USB ports so you can program multiple Teensy devices without physically disconnecting them
	8/18/19	Confirm left_speed is being calculated correctly based on visually counting revolutions
	8/19/19	Publish left_speed ticks/mills and current position to try an debug the variation you are seeing
	8/20/19	average m/s readings and publish left_speed
	8/24/19	Learn to encapsulate objects in 3d prints to encapsulate the magnet
	8/24/19	Redesign gears for a 1:1 ratio and encapsulated magnet
	8/30/19	Redesign odom holder to match new gears.
	8/30/19	Front Axle sensor - test access and programming
	8/30/19	Front Axle sensor - Make usb cable, see which USB port is live, set up udev; Update the compile scripts
	9/1/19	3D model and implement the front axle angle sensor
	9/1/19	Front Axle sensor - write program for publishing cmd_vel angular.z between 1.0 and -1.0
	9/7/19	Steering control - write test program to cycle steering
	9/8/19	Speed Control - Install Ros-Ag tractor simulator and drive from joystick (See Step 4)
	9/8/19	Change .bashrc to have laptop as controller and RPi as master (see Step 6)
	9/8/19	Test that RPi can see cmd_vel from Laptop
	9/8/19	Change FrontAngle to publish integer KLM value
	9/8/19	Change compile_a and compile_b to work on FrontAngle (change on laptop, move to RPi)
	9/8/19	Steering control - write test program to cycle steering using KLM actual
	9/8/19	Steering control - write program to drive steering from cmd_vel angular.z
	9/8/19	Steering control - add failsafe code if angle has not been received
	9/22/19	Change compile_a and compile_b to work on SteerControl (change on laptop, move to RPi)
		Steering Control - Adjust steering control - graph target vs. actual; Adjust Ki in the PID until you get acceptable results.
		Speed Control - Implement PID for the SuperServo to meet the target speed
		Front Axle sensor - implement PID
		Install wireless kill switch
		Research how to set the AS5048B to provide full resolution for only a portion of rotation
		3D print holder for SuperServo for testing
		Change the DIY Joystick to publish PWM insteard of message it so you can message speed related data (e.g. ticks per interval)
		Adjust the max and min PWM extremes based on testing and the speed detected
		Create cable protector for odom holder
		Change a previous listener program to listen for cmd_vel
		Remove Teensy 3.5 from motor holder
		Make a bracket similar to the servo bracket made by your welder
		Setup battery powered RPi/joystick/battery combination; Publish cmd_vel commands.
		Develop code to test internet connection, log it, post to internet and message if it has not been posted.
		Connect 12 volt supply to motor controller
		Have u-joint welded to steering rod
		Rebuild electronics case and mount to frame behind gas tank.
		Run steering motor test
		Read sensor from Teensy connected to RPi
		Make magnet holder with ~6mm magnet
		Make mount for 12 volt blade fuse holder
	12/4/21	Make version 2 of AS5600 holder with IC up and magnet above
		Test reading 3 turn pot on Teensy
		Test 4 speed control for transmission
		Test Jeff's angle and radius detecting software
		Learn Arduino-CLI in order to program Teensy/Nano boards remotely (i.e. while connected to RPi)
		Update low level steering control with new MAP function using results from Jeff's node
		Test drive using updated steer control software
		Print new holder for steer angle sensor that is rain resistant
		Print new holder for left speed monitor sensor that is rain resistant
		Implement battery voltage monitor and alerting
		Connect the sonar sensor Teensy to the RPi
		Reprint and update e-stop switch
		Change RF e-stop to LORA		M0-LORA board - Adafruit

				Reference/Notes/Other products:
				https://learn.sparkfun.com/tutorials/how-to-build-a-remote-kill-switch
				shaft is 15.8 mm (.622 inches)
				Jeff is looking at this IMU: https://www.tindie.com/products/onehorse/ultimate-sensor-fusion-solution-mpu9250/
				Alternate controller: Sabertooth py lib: https://github.com/MomsFriendlyRobotCompany/pysabertooth; Mfg: https://www.dimensionengineering.com/datasheets/Sabertooth2x25v2.pdf
				Flat Push Button Switch Station Box by Uxcell: https://www.amazon.com/Momentary-Green-Button-Switch-Station/dp/B00D0YRX1M
				https://www.swiftnav.com/store/piksi-multi-evaluation-kit/piksi-multi-evaluation-kit-915mhz
				AgBot GPS incline sensor: https://www.mouser.com/ProductDetail/Measurement-Specialties/G-NSDOG2-001?qs=sGAEpiMZZMuV23Z2p9RQbSedHU%2fERWJouXXVy%252bGXduyZx2kAJ8W3qg%3d%3d

				Wireless modem: http://www.winncom.com/en/manufacturer/mikrotik
				U-joint alternative
				3/4" smooth to 5/8" smooth https://sweetmfg.biz/product.php?productid=2565
				16.5mm 36-spline to 3/4" smooth coupler (uses a 7/64 allen wrench from Woodward or epowersteering.com)
				trying: http://www.epowersteering.com/purchase/product/16-5mm-36-to-5-8-u-joint/

## Wiring connections
Teensy Wiring
12V GND Battery	12V+ Blade Fuse Panel	USB Hub	Teensy (3.5) #1	Screw Terminal Strip #1	Screw Terminal Strip #2	Cytron Controller	Steering Motor	Steer Angle Potentiometer	SuperServo 200 Transmission Servo	Odom 1 Sensor	Odom 2 Sensor	Notes
	Slot 1	12V+ Power In					SuperServo has 5 volts from the main 12 volt power line. We just need to supply signal and ground.
X		12V- Power In				Power In -				GND	GND
		Slot 2	micro USB
		Slot 3 (GND)	GND	6		Input GND		Analog GND	GND
			14	5		Input PWM
			16	4		Input DIR
	Slot 2					Power In +
					Motor A out	Red +
					Motor B out	Black -
		Slot 3 (5V)		8				3.3 v
	Slot 3					12V	12V

			20	3				SIGNAL
			4		3				SIGNAL
			7		4					SIGNAL*
			10		5					SIGNAL *

					* include a pullup resistor (10K) and a capacitor to ground (0.1uf)

	V in	7.25
	R1	4,480
	R2	9,950
	V out	5.00

	V in	12.27
	R1	14,480
	R2	9,950
	V out	5.00

## ROBOTs current settings
Area	Part	Item	Sub Item	Matt	Al	Juan	Notes
Operator	System	Human	Bio			Farmer. Agriculture tecnisian and self educated tecnology pac man
			Location		https://goo.gl/maps/38nMJSZjncsAN1uo8	https://goo.gl/maps/F6drKjtuSToLzH8p9
Team		Human			Just me, plus lots of help from Matt, Jeff, Vinney, et. al.	So far ROS community in the net but here in Argentina I'm still working alone, although people always appear willing to contribute and work. The notion that robots are something physical and that you have to touch, is something that plays against us all, thinking about the objective of putting together a team.
Operator Laptop	System	CPU			ThinkPad W530 2.6Ghz 16GB	Asus VivoBook
		Base OS		Ubuntu 16.04	Ubuntu 16.04	Ubuntu 18.04.5 LTS
		Software	ROS OS	Kinetic	Kinetic	Docker Ubuntu Kinetic image
			bash.rc			.bashrc
			start up procedure		link
			operator GUI		ros_start_up.py
			start sensors		teensy_launch.launch
			lawn_tractor.urdf.xacro		lawn_tractor.urdf.xacro	lawn_tractor.urdf.xacro
			farm.yaml		farm.yaml	farm.yaml
			joystick.launch		roslaunch tractor_teleop drive.launch	joystick.launch
			nmea_serial_driver.launch		nmea_serial_driver.launch	nmea_serial_driver.launch
			nav.launch		lawn_tractor.launch	nav.launch
			gps_odom		gps_odom.py
			pure_pursuit.launch			pure_pursuit.launch
			gps_to_pose.launch			gps_to_pose.launch
			gps_heading.py			gps_heading.py
			Time		Chrony	CPU Time + Chrony
			Back Up			Docker Hub
			teb_local_planner_params_carlike.yaml		param file
		Game Pad
		Safety
	Network	Network ID Lan
		VPN			zerotier.com	zerotier.com
		VPN ID
SIM	System
		Base OS		Ubuntu 16.04.7 LTS		Ubuntu 16.04.7 LTS
		Software	ROS OS	kinetic		kinetic
			ROS URDF file		link	urdf.xacro
			Game Pad			Logitech Gamepad F310
			VNC
			Time			System
			Safety (BackUp)
	Network	Network ID Lan
		VPN
		VPN ID
Tractor Robot	Mechanics	Tractor	Model	Cadet XT1 18Hp	Cub Cadett XT1 18HP	Poulan
			Transmission	Hydrostatic	Hydrostatic	Hydrostatic
			Electrical circuit voltage	12 v	12 v	12 v
			Security
			Tyres
	System	CPU Main		RPI3B	RPI3B	RPI3B
		Base OS		Ubuntu Ubiquiti Image	Ubuntu Ubiquiti Image	Ubuntu Ubiquiti Image	VRS ?
		Software	bach.rc
			ROS OS	Kinetic	Kinetic	Kinetic
			ROS URDF file		ROS_Ag
			Time
			Network ID
			Security	WEP
			VNC Server
			Teensy 3.2 Test (Blink)			Teensy 3.2 Test (Blink)
			steer motor control		link
			steer angle sensor		link
			transmission control		link	Cronie
		CPU Electronics Sensors		Teensy 3.2	Teensy 3.2 and 3.5	Teensy 3.2
		CPU Electronics Firmware VRS		?	?	?
		Safety
	Electronics	Drivers Electric	8 channel relay	Yes		Yes
		Drivers Mechanics	Steering motor	Saturn/Chevy steering motor	Saturn/Chevy steering motor	Etios/Toyota steering motor
			Actuator Transmission	transmission SuperServo200	transmission SuperServo200 w/ Teensy	transmission SuperServo200
			Actuator Engine Throttle		manual	NO
		Sensors	Speed encoders		Rear wheel (2) AMS-5048B magnetic	LJ18A3-8Z/EX
			Wheel Encoder	NPN NO DC 6-36V Cylinder Type		NPN NO DC 6-36V Cylinder Type
			GPS Unit	Ardusimple	Com Nav K503	Swiftnav Piksi Multi
			GPS Antena	Survey		Swiftnav 2x L1/L2/L5 GPS/GLN/BDS survey antenna
			GPS Trasmission method			FreeWave radio modem
			IMU		none	Swiftnav Piksi Multi
			Steering potenciometer	3 Turn Potentiometer		3 Turn Potentiometer
			Angle sensor		AMS-5048B magnetic
	Safety LINK		Fuse	Yes		Yes
			kill switch	Yes	Yes, 413Mhz, 50 foot distance	Yes
			ESTOP	Yes		Yes

GPS Base Station	GPS Unit			Ardusimple	Com Nav K503	Swiftnav Piksi Multi
	GPS Antena					Swiftnav 2x L1/L2/L5 GPS/GLN/BDS survey antenna
	Trasmission method			Eth	3DR Radio	FreeWave radio modem
	Network Connected					Yes
	VPN
Current situation					Able to run 2D nav goal in simulator; Waiting on weather to clear to test 2D nav goal outside. 12/13/20 Testing unsuccessful, changes made to time syncing, weather delayed again.	After a short circuit I lost control of the robot. I'm slowly recovering the systems. Having children of school age, the context that the pandemic imposes on me is greatly limiting the time I can dedicate to the project. Although I believe that the problems that I am facing are mainly my own fault and due mostly to my poor documentation of the processes. And for this reason my best efforts are directed to documenting, sharing and comparing.
Past situation

Achivements	Area	Description			Al
	Operator Laptop	OS and ROS loaded

	Simulator	Run 2D Nav goal in RVIZ
		Map developed

	Tractor Robot	Run 2 waypoint AB line test with 2 lat/lon cooridinates with only steering control while I sit on the tractor for safety while logging data. The cross track error should be +/- 2 inches.
		Replay AB line test with the ability to look at key variables (e.g. cross track error and steering PWM signals that were sent)
		Run a multi waypoint test with at least 10 lat/lon cooridinates with only steering control while I'm on the tractor for safety while logging data.
		Connect the Arduino to my companion computer and test throttle control using the gamepad
		Craft a mission plan for a field giving basic information about the field and the type of path I want to run.
		Simulate running a mission plan for a given field.
		Run a multi waypoint test with at least 10 lat/lon cooridinates with steering control and throttle while I'm on the tractor for safety while logging data.
		Run a multi waypoint test with at least 10 lat/lon cooridinates with steering, throttle and brake control while I'm on the tractor for safety while logging data.
		Run a defined mission with steering, throttle and brake control.
	Base Station	Corrections transmitted

Computers used					Tractor – Ubuntu 20.04 / Noetic
					Operator – W10
					Operator – Ubuntu 20.04/Noetic
					Test Machine (aka Tractor2) – Ubuntu 20.04 / Noetic; WS’s – catkin_main, catkin_gazebo_sim, catkin_pico_degree

			Catkin workspaces
			Remote Access via RealVNC
			Backup workspaces to NAS
			Pushed to Github
			OS
			ROS Distro

			Store production Arduino/TTGO code on “Tractor” in folder ?? and push copies to Github repository (e.g. lawn_tractor_embedded_code). I use Arduino IDE because VSCode (I don’t remember why).

			Before rebuilding
			Copy Document folder to NAS
			Copy catkin folders to NAS

			IDE
			Preferred VSCode
			Use Arduino for uploading when needed
			Use manual github push process basically as a backup

## Milestones
Milestone
Steering Hardware
Transmission Hardware
Laptop Hardware
12 Volt Setup
Tractor GPS Setup
Base Station GPS Setup
Tractor Relay Hardware
eStop Hardware
Tractor TTGO LoRa Hardware
RC TTGO LoRa Hardware
Tractor Electronics Board Setup
Setup breakout board for TTGO

Ubuntu 20.04 installed
Base ROS installed
ROS Ag components installed

Testing
Steering
Radio Control
Transmission
GPS RTK, NMEA
2D Nav Goal